## worksheet
| Feature 1: Filter |  | Timeline - 1 month
1 | AI-Based Image Enhancement (Platform-Specific)
| Android | ios
| Tools: | Tools:
| ML Kit (Google) | CoreML
| TFLite (TensorFlow Lite) models for super-resolution, denoising, etc. | Vision Framework
| Tasks: | Tasks:
| Add ML Kit or TFLite dependencies to androidApp | Convert TFLite model to CoreML (.mlmodel)
| Load image into a Bitmap | Use Vision or CoreML to run image through enhancement model
| Preprocess image for model input (resize, normalize) | Use VNCoreMLModel to process the image
| Run model inference using Interpreter | Convert CIImage back to UIImage and show result
| Convert output tensor to Bitmap and return | Use coremltools (Python) to convert models if needed.
Integrate with ImageProcessorImpl as platform-specific logic
2 | Background Removal (Platform-Specific AI)
| Android | ios
| Tools: | Tools:
| ML Kit Segmentation API | VisionKit (for person segmentation)
| TFLite bodypix / deeplab model | CoreML + DeepLabV3
| Tasks: | Tasks:
| Add ML Kit Selfie Segmentation dependency | Use VNGeneratePersonSegmentationRequest
| Pass camera frame or image to segmentation model | Extract alpha mask from result
| Get alpha mask and composite foreground over new background | Composite original image over transparent or replaced background
| Replace background with solid color, blur, or image | Render to UIImage and return
3 | Real-Time Filter Preview
| Android | ios
| Tools: | Tools:
| CameraX + OpenGL / OpenCV | AVCaptureVideoDataOutput
| GPUImage / RenderScript (deprecated) | CoreImage (CIFilter)
| Tasks: | Metal (for high performance)
| Set up CameraX to get camera frames | Tasks:
| Use ImageAnalysis to get real-time frames | Set up AVCaptureSession to capture frames
| Apply filters using OpenCV or OpenGL | Convert each frame to CIImage
| Display in a PreviewView or custom SurfaceView | Apply filter with CIFilter (real-time)
| Optimize frame rate (>= 30fps for smooth UX) | Display filtered image in a CALayer or MetalView
Maintain frame rate and performance
4 | Save Result to File (Image or Video)
Save filtered images/videos locally (for sharing or exporting).
expose a method in shared code
| Android | ios
| Use FileOutputStream to write files. | Use FileManager to write to the app’s sandbox or temp directory.
| Save in Pictures or Movies directory using MediaStore. | For videos, you can write to .mov or .mp4 format.
| Ensure storage permissions (Scoped Storage on Android 10+). | Use UIImageJPEGRepresentation or AVAssetExportSession.
5 | Slider to Control Filter Intensity
Let users adjust strength of filters like blur, brightness, or contrast.
| Android | ios
| Use Slider in Jetpack Compose or SeekBar in XML. | Use SwiftUI Slider or UISlider.
| Bind slider value to intensity in FilterConfig. | Bind to a Float/Double value.
| Pass it to your filter function: | Pass intensity to FFmpeg or CoreImage filter
6 | Realtime FPS Monitoring
Measure performance and ensure smooth real-time rendering (especially with live camera filters).
| Android | ios
| Use Choreographer or count frames in a Handler over time. | Use CADisplayLink to track frame rendering.
| Sample method | Track frame count per second and log/display it.
7 | Multi-platform Toggle for Filters
Allow users to turn filters on/off or switch between modes using a consistent shared interface.
| Android | ios
| Bind to toggle switch in UI (Compose / SwiftUI). | Bind to toggle switch in UI (Compose / SwiftUI).
| Conditionally run filters: | Conditionally run filters:

## baseTool
Use Kotlin Multiplatform
Git Location:
Add tools and versions, which you are going to use